## Sheet1
S.No | Activity | Description | Comments / Sample
1 | Logo Change | Replace Nubekins logo | Logo will be shared by Ram |  | I Renamed inet solution to nubekins
2 | Courses screen | It should be in the format | Cloud | AWS | I added data to json file - Done
|  |  |  | Azure | I added data to json file - Done
|  |  |  | Google Engine | I added data to json file - Done
|  |  |  | IBM BlueMix | I added data to json file - Done
|  |  | Micro soft | MVC | I added data to json file - Done
|  |  |  | ASP .NET | I added data to json file - Done
|  |  |  | C# | I added data to json file - Done
3 | Search Courses | Implement the option course search |  |  | Pending
4 | About US | Seems to be Home Screen. So need to change this |  |  | pending
5 | BackGround Image | Reduce the size of the background image |  |  | Done
6 | Technology Brands | Technology brands can be removed |  |  | Done
7 | Registration panel | As of now we can remove the course registration panel. Since database is yet to be added |  |  | Done
8 | Blog | As of now we can remove the Blog screen as well |  |  | Done
9 | Account | As of now hide Account button |  |  | Done
10 | Course Contents | Place the suitable image in the background with respect to courses |  | For Exmaple, If we choose AWS, then background image should be AWS | Done
11 | Course Description | Place background images against the courses in course description screen. |  |  | Done
12 | Site - Color Change | Now we have changed the logo color. So we need to change the site color also. |  |  | Pending