## Change Request
S.No | Existing Functionality | Change Request | Comments | Stauts
1 | Right now we are keeping separate button for login and register. But the popup is applicabel for both login and register page. | We need to keep a single button like Login/ Register. |  | Completed
2 | In home screen we are showing phone number and address for location. | While clicking phone number or address we need to redirect contact screen. |  | Completed
3 | Right now website name is showing "Inet Solution". | We need to change the name as "Inet Solutions". In all the places we need to change the name. |  | Completed
4 | In mobile view while clicking Login link its not working properly. | We need to fix popup issues. We will discuss this issue. (In Web it's working fine) |  | Completed
5 | Search textbox and search icon is showing right now in home screen. But nothing is performing in that. | We need to remove both icon and textbox. |  | Completed
6 | While mouse hover we need to do some animation for the below text availnbale in home screen. "We are unique because we feature" | We need to do some animation.We will discuss. | I change design something, you look at and share your comments | Completed

## Requirements
S.No | Requirements | Comments | Status
1 | We need course details to add the courses.
2 | Whatever links they want to add , We need the account details to link. Ex: Facebook, Google+, Twitter, Youtube, etc…
3 | If you want to change any images, We need the image and the details where we need to change the images. Ex: Logo , Backgroung images , etc…
4 | While clicking course detail we need to show the details of the course.